## Risk framework
Project name
Prepared by: |  |  |  | Approved by: |  |  |  | Date approved: |  | Risk register review date
Date prepared: | [9 empty] | Reporting Dates
Risk category | Risk category number | RISK: Describe the risk | Impact | Likelihood | Consequence | Risk Rating | CURRENT CONTROLS (Plan A) | Treatment | Plan B (complete for Treat) Notes (complete for Tolerate, Transfer or Terminate) | Likelihood | Consequence | Residual Risk Rating | Review of Risk | Responsibility
Operational risk | 1 | Unplanned emerging interests and priorities soak up resources, resulting in less than 25% of the goals from the project being met | Delay/damage to delivery of project; loss of reputation; reduced staff morale and possibly decreased productivity; potentially not meet funding deliverables, inabilty to meet funding reporting requirements; faliure to met legal, statutory, regulatory and consitutional requirements; | Possible | Major | High | Regular project reporting; emerging interests and changes to priorities are discussed at board meeting for consideration | Treat | Review and assess probability of completing operational plan deliverables. Ensure board are fully briefed on impacts and risks (financial, reputational) from prioritising resources on emerging issues and priorities above agreed operational plan elements. Enhance operational plan reporting requirements to understand capacity and impacts from approved changes to operational plan | Unlikely | Moderate | Medium | Six monthly | CEO Board
Information security risk | 2 | Security breach of member data base results in private and sensitive member data shared to a third party. | Potential personal safety, wellbeing and mental health impacts to members impacted by the breach; organisation reputational damage; loss of membership; potential loss of funding | Unlikely | Extreme | High | Enhanced security features on member data base; limited staff access. | Tolerate | Frequent review of security features, enhanced budget allocation on security systems and backup. |  |  |  | Every six months | CEO Board

## Inputs
| Risk categories | Summary of type | [12 empty] | Lookup | Consequence | Likelihood | Risk
| Operational risk | improper process implementation, failures in systems, insufficient resources, lack of training, etc | [12 empty] | InsignificantAlmost certain | Insignificant | Almost certain | Medium (11)
| Schedule risk | poor project schedule planning, control of timelines, or failure to consider factors that might impact on time | [10 empty] | Extreme | Almost Certain | MinorAlmost certain | Minor | Almost certain | High (16)
| Budget risk | incorrect budget estimations, poor control of purchasing processes, increased costs from project scope creep or change in project scope | [10 empty] | Major | Likely | ModerateAlmost certain | Moderate | Almost certain | High (20)
| Business risk | poor contract management or purchasing controls | [10 empty] | Moderate | Possible | MajorAlmost certain | Major | Almost certain | Very high (23)
| Technical environment risk | risks relating to the environment where business or project operates | [10 empty] | Minor | Unlikely | ExtremeAlmost certain | Extreme | Almost certain | Very high (25)
| Information security risk | poor control of confidentiality/privacy, inadequate measures to control access | [10 empty] | Insignificant | Rare | InsignificantLikely | Insignificant | Likely | Medium (7)
| Programmatic risk | risks considered outside of project team control, such as board decision to close project, government rule changes, changing external environments | [10 empty] | n/a | n/a | MinorLikely | Minor | Likely | Medium (12)
| Infrastructure risk | poor planning of infrastructure and resources to enable project or business | [12 empty] | ModerateLikely | Moderate | Likely | High (17)
| Quality and process risk | inadequate measures in place to identify quality issues or manage risk, poor training of project team members in this area, etc | [12 empty] | MajorLikely | Major | Likely | High (21)
| Resource risk | poor planning of resource requirements to facilitate successful project | [12 empty] | ExtremeLikely | Extreme | Likely | Very high (24)
| Supplier risk | risks associated with suppliers central to project success, ie, delays in delivery of inputs | [12 empty] | InsignificantPossible | Insignificant | Possible | Low (4)
| Technology risk | risks related to outdated technology risk or replacement of technology | [12 empty] | MinorPossible | Minor | Possible | Medium (8)
| Technical and architectural risk | often associated wth project management risks, impacting functionality and performance | [12 empty] | ModeratePossible | Moderate | Possible | High (15)
[15 empty] | MajorPossible | Major | Possible | High (18)
|  |  |  | Consequence | [10 empty] | ExtremePossible | Extreme | Possible | High (22)
|  | Liklihood | Unlikely | Minor | Low | Treat | [8 empty] | InsignificantUnlikely | Insignificant | Unlikely | Low (2)
|  |  | Possible | Moderate | Medium | Tolerate | [8 empty] | MinorUnlikely | Minor | Unlikely | Low (5)
|  |  | Likely | Major | High | Transfer | [8 empty] | ModerateUnlikely | Moderate | Unlikely | Medium (9)
|  |  | Almost certain | Catastrophic | Very High | Terminate | [8 empty] | MajorUnlikely | Major | Unlikely | Medium (13)
[15 empty] | ExtremeUnlikely | Extreme | Unlikely | High (19)
[15 empty] | InsignificantRare | Insignificant | Rare | Low (1)
[5 empty] | Risk Rating Matrix | [9 empty] | MinorRare | Minor | Rare | Low (3)
[8 empty] | Consequences | [6 empty] | ModerateRare | Moderate | Rare | Medium (6)
[7 empty] | a | Extreme | Major | Moderate | Minor | Insignificant |  |  | MajorRare | Major | Rare | Medium (10)
[6 empty] | Likelihood | Almost Certain | Very High | Very High | High | High | Medium |  |  | ExtremeRare | Extreme | Rare | Medium (14)
[7 empty] | Likely | Very High | High | High | Medium | Medium
[7 empty] | Possible | High | High | High | Medium | Low
[7 empty] | Unlikely | High | Medium | Medium | Low | Low
[7 empty] | Rare | Medium | Medium | Medium | Low | Low
Password : Locked